## Emb
Humin jeanswear(Pty)Ltd | [6 empty] | 2009-10-26
Embroidery machine (1) Production progress | [5 empty] | Eff= | 130% | 0%
Order | Part | # | Tables /day | Cut and Transf. in | Total tables | Total produced | Prod Day shift | Prod Night shift | Balance | Days Remaining
9620 | Bp R | 4144 | 190 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9620 | Bp L | 4144 | 260 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 4692 | 625.6 | 249 | 208 | 0 | 376.6
[8 empty] | Days input= | 2.3537
Embroidery machine (2) Production progress | [5 empty] | Eff= | 166.7% | 0%
Order | Part | # | Tables /day | Cut and Transf. in | Total tables | Total produced | Prod Day shift | Prod Night shift | Balance | Days Remaining
9626 | Bp | 4141 | 160 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9627 | Bp | 4145 | 70 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  |  | 2420 | 322.6667 | 206 | 100 | 0 | 116.6667
[8 empty] | Days input= | 1.9444
Zero values

## Prod A
HUMIN JEANSWEAR(Pty)Ltd | [8 empty] | 2009-10-26
(A) Production progress | [8 empty] | CUTTING | [7 empty] | MACHINING |  |  |  | DESPATCH |  | #REF!
Order | Style | # | Hour value | Prod /day | Del. Date | Input Date | Ex-Fact date | Rec. Date | Units Req. |  | Outwork type | Transf. in | Total cut | Prod today | Bal. to cut | O/W Comp | Transf. in | Total produced | Prod today | Balance | Despatched | Balance
9526 | PB91166 S3V-LS | 4139 | 0.747 | 1210 | 2009-11-10 | In Line | 2009-10-27 | 2009-10-19 | 945 | 0 | - | 945 | 949 | 0 | 0 | - | 949 | 949 | 0 | 0 | 540 | 406 | #N/A
9600 | WBY92213 S3V-FB | 4150 | 1.035 | 870 | 2009-11-13 | In Line | 2009-11-04 | 2009-10-19 | 5100 | 0 | - | 5100 | 5100 | 0 | 0 | - | 5100 | 272 | 0 | 4828 | 0 | 269 | #N/A
9610 | PM94501 S2H-LS-LGY | 3222 | 0.929 | 970 | 2009-11-10 | Cut | 2009-11-09 | 2009-10-20 | 2436 | Emb | Emb | 2436 | 2420 | 0 | 16 | No | Emb not rec. | 0 | 0 | 0 | 0 | 0 | #N/A
9614 | PM97447 S3V-FB | 3224 | 0.838 | 1080 | 2009-11-17 | In House | 2009-11-11 | 2009-10-22 | 2048 | 0 | - | 2048 | 0 | 0 | 2048 | - | 0 | 0 | 0 | 0 | 0 | 0 | #N/A
9626 | WGO61113 S3V | 4141 | 0.671 | 1350 | 2009-11-27 | In House | 2009-11-17 | 2009-10-22 | 5100 | Emb | Emb | 5100 | 0 | 0 | 5100 | No | Emb not rec. | 0 | 0 | 0 | 0 | 0 | #N/A
9668 | WWM91105 S3V | 3119 | 0.57 | 1590 | 2009-12-10 | 2009-11-09 | 2009-11-18 | - | 749 | 0 | - | not rec.
9669 | WWM91105 S3V | 3119 | 0.57 | 1590 | 2009-12-10 | 2009-11-09 | 2009-11-18 | - | 170 | 0 | - | not rec.
9630 | WBI01115 S3V-LS-LSN-C | 4152 | 0.55 | 1640 | 2009-11-27 | 2009-11-10 | 2009-11-23 | - | 4590 | 0 | - | not rec.
9629 | WBI01113 S2V-CA | 4149 | 0.565 | 1600 | 2009-11-28 | 2009-11-12 | 2009-11-26 | - | 4590 | 0 | - | not rec.
| #N/A | avg. | 39.9144 | minute jean |  |  |  |  | 66177 |  |  | 17969 | 10809 | 0 | 7164 |  | 8389 | 3561 | 910 | 4828 | 2877 | 675
| #N/A | /day | 1432.1899 | [8 empty] | 5.0021 | Days cutting for A |  |  |  | 10.6535 | 8.6535 | Days input |  | Total Fact. to Dispatch | 4932
#N/A
| #N/A | [10 empty] | 2.9471 | Days to cut-Factory |  |  |  |  | 7536 | Emb+Print O/W outstanding
#N/A
| #N/A | [10 empty] | 25306 | Units to cut-Factory |  |  |  |  | 0 | Rivit outwork outstanding
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## Prod B
HUMIN JEANSWEAR(Pty)Ltd | [8 empty] | 2009-10-26
(B) Production progress | [8 empty] | CUTTING | [7 empty] | MACHINING |  |  |  | DESPATCH |  | #REF!
Order | Style | # | Hour value | Prod /day | Del. Date | Input Date | Ex-Fact date | Rec. Date | Units Req. |  | Outwork type | Transf. in | Total cut | Prod today | Bal. to cut | O/W Comp | Transf. in | Total produced | Prod today | Balance | Despatched | Balance
9613 | WBY91103 S3V-FB | 4143 | 0.914 | 990 | 2009-11-24 | In Line | 2009-11-03 | 2009-10-16 | 7140 | 0 | - | 7140 | 7141 | 0 | 0 | - | 7141 | 3250 | 0 | 3891 | 2230 | 1017 | #N/A
9599 | PM95402 S1H-FA-OV | 3226 | 0.944 | 960 | 2009-11-10 | In House | 2009-11-05 | 2009-10-26 | 2205 | 0 | - | 2205 | 0 | 0 | 2205 | - | 0 | 0 | 0 | 0 | 0 | 0 | #N/A
9615 | PM91560 S2V-BALL | 3195 | 0.853 | 1060 | 2009-11-17 | In House | 2009-11-10 | 2009-10-23 | 2362 | 0 | - | 2362 | 360 | 0 | 2002 | - | 360 | 0 | 0 | 360 | 0 | 0 | #N/A
9596 | PM91560 S3V | 3195 | 0.853 | 1060 | 2009-11-24 | 2009-10-29 | 2009-11-12 | - | 2100 | 0 | - | not rec. | [8 empty] | 0 |  | #N/A
9620 | WGO61512 S3V-LS-C | 4144 | 0.959 | 940 | 2009-11-23 | 2009-10-29 | 2009-11-19 | - | 4080 | Emb | Emb | not rec. | [8 empty] | 0 |  | #N/A
9664 | WBO91122 TBC | NEW | 0.656 | 1370 | 2009-11-27 | 2009-11-05 | 2009-11-25 | - | 4590 | Emb | Emb | not rec. | [10 empty] | #N/A
9650a | WWM91111 S3V-LS | 3225 | 1.066 | 850 | 2009-12-10 | 2009-11-11 | 2009-11-26 | - | 575 | Emb | Emb | not rec.
| #N/A | avg. | 50.0182 | minute jean |  |  |  |  | 55794 |  |  | 11707 | 7501 | 360 | 4207 |  | 7501 | 3250 | 1100 | 4251 | 2230 | 1017
| #N/A | /day | 1176.1724 | [8 empty] | 3.5769 | Days cutting for B |  |  |  | 7.8049 | 5.8049 | Days input |  | Total Fact. to Dispatch | 4932
#N/A
| #N/A | [10 empty] | 2.9471 | Days to cut-Factory |  |  |  |  | 0 | Emb+Print O/W outstanding
#N/A
| #N/A | [10 empty] | 25306 | Units to cut-Factory |  |  |  |  | 0 | Rivit outwork outstanding
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## Prod C
HUMIN JEANSWEAR(Pty)Ltd | [8 empty] | 2009-10-26
Line (C) Production progress | [8 empty] | CUTTING | [7 empty] | MACHINING |  |  |  | DESPATCH |  | #REF!
Order | Style | # | Hour value | Prod /day | Del. Date | Input Date | Ex-Fact date | Rec. Date | Units Req. |  | Outwork type | Transf. In | Total cut | Prod today | Bal. to cut | O/W Comp | Transf. in | Total produced | Prod today | Balance | Despatched | Balance
9578 | PL61456 S1V | 1051 | 0.656 | 1380 | 2009-10-27 | In Line | 2009-10-27 | 2009-10-15 | 2397 | Emb | Emb | 2397 | 2397 | 0 | 0 | Yes | 2397 | 2176 | 0 | 221 | 1250 | 923 | #N/A
9595 | PM91560 S3V | 3195 | 0.853 | 1060 | 2009-10-26 | In Line | 2009-10-30 | 2009-10-16 | 2346 | 0 | - | 2346 | 2416 | 0 | 0 | - | 2416 | 0 | 0 | 2416 | 0 | 0 | #N/A
9572A | PB91139 S3V-LGY | 496 | 0.815 | 1110 | 2009-10-12 | Cut | 2009-11-02 | 2009-10-20 | 1672 | 0 | - | 1672 | 1672 | 0 | 0 | - | 1672 | 0 | 0 | 1672 | 0 | 0 | #N/A
9572B | PB91139 S3V-LGY | 496 | 0.815 | 1110 | 2009-10-12 | Cut | 2009-11-03 | 2009-10-20 | 1028 | 0 | - | 1028 | 1028 | 0 | 0 | - | 1028 | 0 | 0 | 1028 | 0 | 0 | #N/A
9572C | PB91139 S3V-LGY | 496 | 0.815 | 1110 | 2009-10-12 | Cut | 2009-11-04 | 2009-10-21 | 651 | 0 | - | 651 | 651 | 0 | 0 | - | 651 | 0 | 0 | 651 | 0 | 0 | #N/A
9625 | WGO61112 S3V | 4140 | 0.671 | 1350 | 2009-11-27 | Cut | 2009-11-10 | 2009-10-12 | 5100 | Emb | Emb | 5100 | 5100 | 0 | 0 | Yes | 5100 | 0 | 0 | 5100 | 0 | 0 | #N/A
9612 | WGO61511 S4B | 4142 | 0.671 | 1350 | 2009-11-16 | Cut | 2009-11-16 | 2009-10-21 | 5100 | Emb | Emb | 5100 | 4692 | 0 | 408 | No | Emb not rec. | 0 | 0 | 0 | 0 | 0
9627 | WGY61510 S2V | 4145 | 0.565 | 1600 | 2009-11-27 | 2009-10-29 | 2009-11-19 | - | 4284 | Emb | Emb | not rec.
9658 | WGY61510 S2V | 4145 | 0.565 | 1600 | 2009-12-25 | 2009-11-04 | 2009-11-20 | - | 2040 | Emb | Emb | not rec.
9619 | WBO91120 TBC | NEW | 0.656 | 1420 | 2009-11-23 | 2009-11-12 | 2009-11-26 | - | 4794 | 0 | - | not rec.
9628 | WBY91105 S3V-LS-C | 4148 | 0.565 | 1600 | 2009-11-27 | 2009-11-17 | 2009-12-01 | - | 4080 | 0 | - | not rec.
| #N/A | avg. | 38.2039 | minute jean |  |  |  |  | 72055 |  |  | 18294 | 17956 | 2358 | 408 |  | 13264 | 2176 | 1136 | 11088 | 1250 | 923
| #N/A | /day | 1510.8404 | [8 empty] | 0.27005 | Days cutting for C |  |  |  | 8.9738 | 6.9738 | Days input |  | Total Fact. to Dispatch | 4932
#N/A
| #N/A | [10 empty] | 2.9471 | Days to cut-Factory |  |  |  |  | 5100 | Emb+Print O/W outstanding
#N/A
| #N/A | [10 empty] | 25306 | Units to cut-Factory |  |  |  |  | 0 | Rivit outwork outstanding
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A

## Prod D
HUMIN JEANSWEAR | [8 empty] | 2009-10-26
Line (D) Production progress | [8 empty] | CUTTING | [7 empty] | MACHINING |  |  |  | DESPATCH |  | #REF!
Order | Style | # | Hour value | Prod /day | Del. Date | Input Date | Ex-Fact date | Rec. Date | Units Req. |  | Outwork type | Transf. In | Total cut | Prod today | Bal. to cut | O/W Comp | Transf. in | Total produced | Prod today | Balance | Despatched | Balance
9644 | WGI31101 NO WASH | 4117 | 0.149 | 1800 | 2009-11-25 | In Line | 2009-10-23 | 2009-10-08 | 5000 | 0 | - | 5000 | 5000 | 0 | 0 | - | 5000 | 5000 | 0 | 0 | 4600 | 397 | #N/A
9645 | WGI31102 NO WASH | 4117 | 0.149 | 1800 | 2009-11-28 | In Line | 2009-10-30 | 2009-10-12 | 5500 | 0 | - | 5500 | 5500 | 0 | 0 | - | 5500 | 1923 | 0 | 3577 | 0 | 1920 | #N/A
9640 | WBI31101 NO WASH | 4118 | 0.149 | 1800 | 2009-11-23 | In House | 2009-11-04 | 2009-10-20 | 5300 | 0 | - | 5300 | 2432 | 0 | 2868 | - | 2432 | 0 | 0 | 2432 | 0 | 0 | #N/A
9636 | WBI31101 NO WASH | 4118 | 0.149 | 1800 | 2009-11-23 | In House | 2009-11-10 | 2009-10-26 | 6936 | 0 | - | 6936 | 0 | 0 | 6936 | - | 0 | 0 | 0 | 0 | 0 | 0 | #N/A
9638 | WBI31101 NO WASH | 4118 | 0.149 | 1800 | 2009-11-23 | 2009-11-03 | 2009-11-16 | - | 6018 | 0 | - | not rec. | [8 empty] | 0 |  | #N/A
9642 | WBI31101 NO WASH | 4118 | 0.149 | 1800 | 2009-11-23 | 2009-11-05 | 2009-11-18 | - | 4102 | 0 | - | not rec. | [10 empty] | #N/A
9646 | WGI31102 NO WASH | 4117 | 0.149 | 1800 | 2009-12-26 | In House | 2009-12-07 | 2009-10-19 | 3723 | 0 | - | 3723 | 0 | 0 | 3723 | - | 0 | 0 | 0 | 0 | 0 | 0 | #N/A
9648 | WGI31102 NO WASH | 4117 | 0.149 | 1800 | 2009-12-26 | 2009-11-30 | 2009-12-09 | - | 2878 | 0 | - | not rec. | [10 empty] | #N/A
9660 | WBI31101 NO WASH | 4118 | 0.149 | 1800 | 2009-12-26 | 2009-12-01 | 2009-12-11 | - | 4386 | 0 | - | not rec.
9661 | WBI31101 NO WASH | 4118 | 0.149 | 1800 | 2009-12-26 | 2009-12-03 | 2009-12-15 | - | 3060 | 0 | - | not rec. | [10 empty] | #N/A
| #N/A | avg. | 8.94 | minute jean |  |  |  |  | 64846 |  |  | 26459 | 12932 | 2432 | 13527 |  | 12932 | 6923 | 1325 | 6009 | 4600 | 2317 | #N/A
| #N/A | /day | 1800.3356 | [8 empty] | 2.0951 | Days cutting for D |  |  |  | 5.4328 | 3.4328 | Days input |  | Total Fact. to Dispatch | 4932
#N/A
| #N/A | [10 empty] | 2.9471 | Days to cut-Factory |  |  |  |  | 0 | Emb+Print O/W outstanding
#N/A
| #N/A | [10 empty] | 25306 | Units to cut-Factory |  |  |  |  | 0 | Rivit outwork outstanding
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A